## Roadmap (Auto)
Product Roadmap - 2026-2027 |  |  | Showing 25 of 47 rows | [31 empty] | (All) | (All) | (All) | Theme, then Status
Select Portfolio | Select Theme | Select Status | Sort by
Used | (All) | (All)
[35 empty] | B2B | Improve Discovery | 00. Parking Lot | Status, then Theme
[35 empty] | Used | Increase Trade In Awareness | 01A. Research - Foundational | Dev start (earliest)
Description | Hint: Pick a theme in Show theme above to see its description and measures. | [33 empty] | Find | Improve Trade In User Flow | 01. Prod Discovery | UX start (earliest)
Measure adoption | [35 empty] | Increase Trade In Reactivation | 02. UX Req | Deliverable A-Z
Measure impact | [35 empty] | Increase Buy Used Awareness | 03. UX Discovery
|  | UX | UX work in month | [32 empty] | Improve Buy Used Customer Experience | 04. UX Design
[9 empty] | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 |  |  |  | Increase Buy Used Reactivation | 04A. Research - Design Validation
Product Goal: Grow B2B Platforms, Used and Trade-In verticals while elevating content quality across the site. |  | DEV | Dev sprint | [5 empty] | 2026-01-01: 2026; 2027-01-01: 2027 |  |  |  | Increase B2B Acquisition | 05. Business Review
|  | BOTH | Both, same month | [5 empty] | 2026-01-01: Q1; 2026-04-01: Q2; 2026-07-01: Q3; 2026-10-01: Q4; 2027-01-01: Q1; 2027-04-01: Q2; 2027-07-01: Q3; 2027-10-01: Q4 |  |  |  | Increase The Studio B&H Awareness | 06. Architecture
Theme (swim lane) | Deliverable (BHP Link) | Jira | Status | UX From | UX To | UX Wks | Dev From | Dev To | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | _theme | _row |  | Improve The Studio B&H Customer Experience | 07. Grooming
Increase Trade In Awareness | Decouple Sell Used from Used Hub | BHP-7431 | 01. Prod Discovery |  |  | 0 | 2027-02-01 | 2027-02-28 | 2027-02-01: DEV | Increase Trade In Awareness | 7 |  | Increase Trust & Condition Transparency | 08. Ready for Dev
| Sell Used Mega Menu | BHP-7430 | 01. Prod Discovery | 2026-09-21 | 2026-09-28 | 2 | [26 empty] | Increase Trade In Awareness | 8 |  | Improve Search & Findability | 09. In Dev
| Used Activity Notification | BHP-7237 | 02. UX Req | 2026-09-14 | 2026-09-28 | 3 | 2026-12-01 | 2027-01-31 | 2026-12-01: DEV; 2027-01-01: DEV | Increase Trade In Awareness | 11 |  |  | 10. QA
| Increase Awareness of Trade In Offers - Best Buy Inspiration/Competitive Effort | BHP-6827 | 03. UX Discovery |  |  | 0 | 2026-10-01 | 2026-10-31 | 2026-10-01: DEV | Increase Trade In Awareness | 15 |  |  | 11. UAT
| B2B & Used Visibility in the Nav | BHUX-34378 | 04. UX Design | 2026-06-01 | 2026-09-28 | 18 | 2027-02-01 | 2027-02-28 | 2026-06-01: UX; 2026-07-01: UX; 2026-08-01: UX; 2026-09-01: UX; 2027-02-01: DEV | Increase Trade In Awareness | 26 |  |  | 12. Release
| PDP Purchased in 20XX, Trade In Value is $YYY.YY | BHUX-35309 | 06. Architecture | 2026-08-17 | 2026-08-17 | 1 | 2026-10-01 | 2026-10-31 | 2026-10-01: DEV | Increase Trade In Awareness | 29 |  |  | 13. Live
Improve Trade In User Flow | Sell Used Purchase Look Up | BHP-7236 | 02. UX Req | 2026-08-24 | 2026-09-07 | 3 | 2026-11-01 | 2027-01-31 | 2026-11-01: DEV; 2026-12-01: DEV; 2027-01-01: DEV | Improve Trade In User Flow | 10
| Trade In Email - Comprehensive Refresh Discovery | BHUX-34772 | 04. UX Design | 2026-07-13 | 2026-08-03 | 4 | 2026-10-01 | 2026-10-31 | 2026-07-01: UX; 2026-08-01: UX; 2026-10-01: DEV | Improve Trade In User Flow | 21
| Used - Sell Used Experience | BHUX-33009 | 04. UX Design | 2026-04-20 | 2026-09-28 | 24 | 2027-01-01 | 2027-03-31 | 2026-04-01: UX; 2026-05-01: UX; 2026-06-01: UX; 2026-07-01: UX; 2026-08-01: UX; 2026-09-01: UX; 2027-01-01: DEV; 2027-02-01: DEV; 2027-03-01: DEV | Improve Trade In User Flow | 22
| Sell Used User Flow Design Validation | BHUR-133 | 04A. Research - Design Validation | 2026-07-06 | 2026-09-07 | 10 | [26 empty] | Improve Trade In User Flow | 27
| Used Status Email Update | BHUX-34723 | 06. Architecture | 2026-07-13 | 2026-07-13 | 1 | 2026-10-01 | 2026-10-31 | 2026-10-01: DEV | Improve Trade In User Flow | 28
| Trade In Discrepancy Email Refresh (Copy Only) |  | 09. In Dev | 2026-07-13 | 2026-07-20 | 2 | 2026-09-01 | 2026-09-30 | 2026-09-01: DEV | Improve Trade In User Flow | 37
Increase Buy Used Awareness | Used Hub - Just Added Component | BHP-7229 | 02. UX Req | 2026-08-10 | 2026-09-14 | 3 | 2027-02-01 | 2027-02-28 | 2027-02-01: DEV | Increase Buy Used Awareness | 13
| Used Just Added Page | BHP-7230 | 02. UX Req | 2026-05-18 | 2026-10-12 | 4 | 2027-02-01 | 2027-02-28 | 2027-02-01: DEV | Increase Buy Used Awareness | 14
| Out of stock Alerts for used products | BHUX-35020 | 03. UX Discovery | 2026-08-03 | 2026-08-24 | 4 | 2026-10-01 | 2026-10-31 | 2026-08-01: UX; 2026-10-01: DEV | Increase Buy Used Awareness | 16
| Add New ¦ Used tab to all listing pages and search results pages | BHUX-35303 | 03. UX Discovery | 2026-08-24 | 2026-09-14 | 4 | 2026-11-01 | 2026-11-30 | 2026-08-01: UX; 2026-09-01: UX; 2026-11-01: DEV | Increase Buy Used Awareness | 18
| Add 'shop by popular brands' section to Used Homepage | BHUX-34844 | 04. UX Design | 2026-07-20 | 2026-09-07 | 8 | 2026-11-01 | 2027-01-31 | 2026-07-01: UX; 2026-08-01: UX; 2026-09-01: UX; 2026-11-01: DEV; 2026-12-01: DEV; 2027-01-01: DEV | Increase Buy Used Awareness | 23
| Shop By Popular Brand' Listing Pages Discovery | BHUX-34845 | 04. UX Design | 2026-07-27 | 2026-09-07 | 7 | 2026-11-01 | 2027-01-31 | 2026-07-01: UX; 2026-08-01: UX; 2026-09-01: UX; 2026-11-01: DEV; 2026-12-01: DEV; 2027-01-01: DEV | Increase Buy Used Awareness | 24
| My Account > Trade In Awareness | BHUX-35010 | 04. UX Design | 2026-08-10 | 2026-08-24 | 3 | 2026-12-01 | 2026-12-31 | 2026-08-01: UX; 2026-12-01: DEV | Increase Buy Used Awareness | 25
| Condition Grouping | BHUX-33519 | 13. Live | 2026-04-27 | 2026-05-04 | 2 | 2026-08-01 | 2026-08-31 | 2026-08-01: DEV | Increase Buy Used Awareness | 38
| Used Hub Enhancements | BHUX-31354 | 13. Live |  |  | 0 | [26 empty] | Increase Buy Used Awareness | 47
Improve Buy Used Customer Experience | New Condition Rating Scale | BHUX-33510 | 00. Parking Lot | 2026-06-01 | 2026-06-15 | 3 | 2027-01-01 | 2027-01-31 | 2027-01-01: DEV | Improve Buy Used Customer Experience | 1
| New Condition Rating Scale (Intermediate Step) | BHJ-121278 | 00. Parking Lot |  |  | 0 | 2026-10-01 | 2026-10-31 | 2026-10-01: DEV | Improve Buy Used Customer Experience | 3
| Used Roll Up SKUs | BHP-6479 | 01. Prod Discovery |  |  | 0 | 2026-12-01 | 2027-02-28 | 2026-12-01: DEV; 2027-01-01: DEV; 2027-02-01: DEV | Improve Buy Used Customer Experience | 9
| Actual Used Images | BHP-4563 | 13. Live |  |  | 0 | [26 empty] | Improve Buy Used Customer Experience | 46
How this tab works
• Every row is generated from the UX Weekly tab. Add, edit or delete a row there — Theme #1, Title, Jira, Status and the weekly resourcing cells — and this roadmap redraws itself. Nothing here is typed by hand.
• The cream cells in the control panel are the only cells you edit. Filter by portfolio, theme or status and re-sort with them; the list recompacts, so there are never gaps to scroll past. Portfolio matches partially, so “B2B” also catches “B2B/Used”, and the theme filter looks at both Theme #1 and Theme #2. Set all three back to (All) to see everything.
• Sorting by anything other than Theme breaks the lanes apart on purpose — the theme name then repeats beside each row so you can still see which lane it belongs to.
• Swim lanes = Theme #1, ordered by the Theme list on the Control tab; rows sort by Theme, then Status. Click a theme name to jump to its definition on Control; click a Jira number or a deliverable to open the ticket in Jira.
• Blue “U” means that month contains at least one week resourced to a designer on UX Weekly. Gaps are real — a month with no name in any of its week columns stays blank, so stop-start work reads as stop-start.
• “UX From”/“UX To” are the first and last resourced week; “UX Wks” counts the weeks actually resourced between them. A wide envelope with a low week count means the work is scheduled in separate blocks.
• Green “D” is the dev sprint window from Start Sprint / End Sprint on Dev Tracker, which is month-level rather than weekly. Purple “B” = both in the same month.
• Dev Tracker is row-aligned with UX Weekly (row 12 there is row 12 here), so sprint dates are read directly — no title matching, and nothing can drift out of sync.
• The amber column is the current month. Rows 7–80 are pre-wired, so up to 74 deliverables fit without touching a formula. A Start/End Sprint with no year is read as the current year.
• Deliverable links use the Product Ticket column (L) on Dev Tracker. Add a ticket there for a new row and its link starts working here.
• The theme detail panel under the controls follows the Show theme dropdown and shows that theme's description and measures from the Control tab. Collapse it with the minus sign in the row gutter if you want the space back. Where it says nothing is defined, that is a real gap on Control, not a lookup failure.
• The full theme reference below the notes prints with the sheet, so a shared or printed copy carries the definitions even though the panel only shows one theme at a time.
• Hidden tab “Roadmap Calc (Don’t Touch)” does the lookup, the per-month week test and the sorting. Unhide it to audit; don’t edit it.
Theme reference — pulled live from the Control tab
Theme | Description |  |  |  |  | Measure adoption |  |  | 2026-08-01: Measure impact
Improve Discovery | OG Find initaitives that Jerel still owns |  |  |  |  | Refinement usage rate, Search-to-listing CTR, Mega menu / nav click through rate, Sessions using two or more filters |  |  | 2026-08-01: Listing-to-PDP rate, Zero-result search rate, Search-attributed conversion rate, Time to first PDP view
Increase Trade In Awareness | Surface trade-in as a clear, relevant option at high-intent moments, Order History, PDPs, post-purchase, so customers who own eligible gear know they can trade it in. |  |  |  |  | Trade-in CTA Impressions (Order History/PDP), CTA Click through rate, % of eligible sessions exposed to CTA |  |  | 2026-08-01: New to trade in quote starts, Quote start rate among CTA exposed users, Assisted trade-in revenue (CTA attributed)
Improve Trade In User Flow | Reduce friction in the sell/trade-in submission flow: search, quote, shipping/drop-off, to raise completion and quote-to-conversion rates. |  |  |  |  | % started quotes completed, Time to quote (median), Post-acceptance ststus engagement rate |  |  | 2026-08-01: Quote-to-accepted-offer rate, Drop-off rate by flow step, sell-flow CSAT (isolated), Support contact rate per quote, Payout cycle time (accepted>paid)
Increase Trade In Reactivation | Re-engage past customers with unused eligible gear via triggered emails tied to purchase timing and inventory demand signals. |  |  |  |  | Reactivation email open rate, reactivation email CTR, quote starts attributed to email |  |  | 2026-08-01: Reactivated quote to completion rate, revenue from reactivated sellers, days since last purchase > trade in (trend)
Increase Buy Used Awareness | Grow discovery of the Used Hub and used inventory through SEO, brand listing pages, and internal linking so more shoppers know B&H sells used gear. |  |  |  |  | Organic sessions to Used Hub/brand pages, Search impressions & CTR (used pages), Internal link CTR (New>used cross links), Cross-sell CTA impressions (used alt. on New PDP) |  |  | 2026-08-01: New-to-used buyer sessions, Used PDP views per session, Used share to total category traffic, cross sell attributed used PDP views/purchases
Improve Buy Used Customer Experience | Make used PDPs and listing pages easier to evaluate, increase condition clarity, provide product photos, and filtering, so shoppers can confidently purchase used gear |  |  |  |  | PLP filter usage rate, used pdp engagement rate (photo/spec expansion), order status page engagement rate |  |  | 2026-08-01: Used PDP-to-cart rate, Used cart-to-purchase rate, Post-Purchase CSAT (isolated)
Increase Buy Used Reactivation | Win back past buyers with relevant used-inventory alerts and win-back offers matched to their purchase history |  |  |  |  | Win Back email open rate, win-back email CTR, Browse to used PDP rate from email |  |  | 2026-08-01: Repeat used-purchase rate, Revenue from reactivated buyers, Time-since-last-purchase > repurchase (trend)
Increase B2B Acquisition | Grow the pipeline of registered B2B accounts by making the B2B Hub, EDU and vertical landing pages easier to find and sign up from, so qualifying organisations self-serve rather than routing through sales. |  |  |  |  | Sessions to B2B Hub / EDU / vertical landing pages, Sign-up form starts, Sign-up CTA click through rate, % of B2B sessions reaching a landing page |  |  | 2026-08-01: Completed B2B registrations, Registration-to-first-order rate, New B2B accounts per month, Revenue from newly registered accounts
Increase The Studio B&H Awareness | Build awareness that The Studio is a B&H offering by surfacing B&H branding and cross-links on high-ticket products and Studio entry points, so customers connect the two. |  |  |  |  | Sessions to Studio landing and category pages, B&H awareness module impressions on high-ticket PDPs, Cross-link click through rate, Organic impressions for Studio terms |  |  | 2026-08-01: New-to-Studio sessions, Studio PDP views per session, Studio share of high-ticket category traffic, Assisted Studio revenue
Improve The Studio B&H Customer Experience | Make Studio category, landing and hybrid pages easier to evaluate and navigate, so customers can compare and specify Studio products without leaving for a sales conversation. |  |  |  |  | Studio category page engagement rate, Hybrid page filter usage, Spec / detail expansion rate, Quote or enquiry form starts |  |  | 2026-08-01: Studio PDP-to-cart rate, Enquiry-to-quote rate, Studio CSAT (isolated), Support contact rate per Studio session
Increase Trust & Condition Transparency | Cross-cutting theme covering whether customers believe the grading/condition information is accurate and complete, ties directly to condition rating scale and PDP condition grouping work, and carries COO-level visibility |  |  |  |  | Condition information expansion rate on used PDPs, Actual-image gallery engagement rate, Condition rating scale page views, Filter usage by condition |  |  | 2026-08-01: Used PDP-to-cart rate by condition, Condition-related return rate, Condition-related support contacts per order, Post-purchase CSAT on condition accuracy
Improve Search & Findability | Cross-cutting theme spanning sell-side item search (finding what you own to quote it) and buy-side discovery (finding used inventory to purchase). Flagged as the single highest-priority friction point across VoC research on both sides. |  |  |  |  | Search usage rate (sell and buy side), Refinement usage per search, Typeahead selection rate, Searches per session |  |  | 2026-08-01: Zero-result search rate, Search-to-PDP rate, Search-attributed quote starts (sell side), Search-attributed used purchases (buy side)

## Quaterly (hidden)
2026 Roadmap - Jerel Smith
| Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | Q1 2027 | Q2 2027 | Q3 2027 | Q4 2027 | Q1 2028 | Q2 2028 | Q3 2028 | Q4 2028
1. B2B |  |  |  | Freeze
PMO-5000
>CMS Lite | Discovery | Design + Dev | Dev + Live
>Sign Up | Discovery | Design + Dev | Dev + Live
>Internal Pages | Discovery + Research | Design + Dev | Dev + Live
B2B Hub Health Dashboard |  |  | All
The Studio
Categories | Discovery + Research | Stakeholder Input | Dev + Live
>Landing Page | Discovery + Research | Design + Dev | Dev + Live
>Multi-Page | Discovery + Research
2. Used
Sell Used/Trade In
>Sell Used Experience | Discovery + Research | Design + Dev | Live
>Trade In Experience | Discovery + Research | Design + Dev | Live
Trade In Emails | Discovery |  | …Live
Used Hub Health Dashboard |  | Discovery + Research | …Live
Condition Rating Scale
>New Condition Rating Scale | Discovery | Design | Dev + Live
PDP - Group By Condition | Discovery | Design | Dev + Live
PLP - Roll Up By Condition
Actual Used Images (Tim) | Dev | Operationalize | Live
3. Legacy Find (Submitting to Dev - Not Owning Afterwards)
Mega Menu | Discovery + Research | Design + Dev | Live
Roll Up SKUs | Design + Grooming
Nested Refinements | Discovery + Design | Design | Dev + Live

## Monthly (hidden)
Journey/Initiative | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
Enterprise Platforms & Used | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December
1. B2B | [10 empty] | Freeze
PMO-5000
>Weblogic-> Apeture/JSON Led |  |  | Discovery + Research | Design |  | Dev |  | Live
>Sign Up |  |  | Discovery + Research
>Internal Pages |  |  | Discovery + Research
B2B Hub Health Dashboard |  |  |  | Discovery | Research | Dev | Live
The Studio
Categories |  |  | Discovery + Research | Design | Dev
>Landing Page |  |  | Discovery | Research | Design | Dev
>Multi-Page | [5 empty] | Design | Dev | Dev | Live
EDU | Design |  |  |  | Dev | Live
2. Used
Sell Used/Trade In
>Sell Used Experience |  |  | Discovery + Research | Design | Design | Dev | Dev | Live
>Trade In Experience |  |  | Discovery + Research |  | Design | Dev | …Live
Trade In Emails |  |  | Discovery | Design | Dev | Live
Used Hub Health Dashboard |  |  |  |  | Discovery + Research | Dev | Live
Condition Rating Scale
>New Condition Rating Scale | Discovery | Research | Socialize | Socialize | Dev | Live
PDP - Group By Condition |  |  |  | Design | …Live
PLP - Roll Up By Condition | [6 empty] | Discovery | Research | Live
Actual Used Images (Tim) |  |  |  | Design | Dev | Operationalize | Operationalize | Live
3. Legacy Find (Submitting to Dev - Not Owning Afterwards)
Mega Menu | Discovery | Research | Design |  | …Live
Nested Refinements | Discovery | Research | Design |  | Dev | Live

## UX + Dev
Product | Portfolio | Theme #1 | Theme #2 | Title | Jira | Status | Page Type | Component (GA4) | Component (legacy) | Tech | BHUX | BHJ | BHIA | UNIX | BIDW | BHUR | DBA | WEBC | SEARCH | Start Sprint | End Sprint | Notes | Product Ticket | time axis 2026-04-13 to 2028-01-03
Jerel Smith | Used | Improve Buy Used Customer Experience | Improve Trade In User Flow | New Condition Rating Scale | BHUX-33510 | 00. Parking Lot | productDetail |  |  | BHJ, BHIA, UNIX |  | X | X | X | [5 empty] | Jan 2027 | Jan 2027 |  | BHP-4771 | 2026-06-01: Leo; 2026-06-08: Leo; 2026-06-15: Leo
Jerel Smith | B2B | Increase B2B Acquisition |  | B2B Hub - Logged In B2B Experience | BHP-6901 | 00. Parking Lot | b2bHub |  |  | BHJ |  | X | [7 empty] | Mar 2027 | May 2027 |  | BHP-6901 | 2026-06-08: Jaye; 2026-10-05: Jaye; 2026-10-12: Jaye; 2026-10-19: Jaye; 2026-10-26: Jaye
Jerel Smith | Used | Improve Buy Used Customer Experience | Improve Trade In User Flow | New Condition Rating Scale (Intermediate Step) | BHJ-121278 | 00. Parking Lot |  |  |  | DBA | [6 empty] | X |  |  | Oct 2026 | Oct 2026 |  | BHP-7238 | bar: 2026-04-13 to 2026-05-25
Jerel Smith | B2B | Improve The Studio B&H Customer Experience |  | B2B - The Studio Categories | BHUX-33434 | 01. Prod Discovery | b2bHub |  |  | BHJ |  | X | [7 empty] | Dec 2026 | Jan 2027 |  | BHP-6446 | 2026-04-20: Hilli; 2026-05-04: Hilli; 2026-06-08: Hilli; 2026-08-31: Hilli; 2026-09-07: Hilli; 2026-09-14: Hilli
Jerel Smith | B2B | Increase The Studio B&H Awareness |  | The Studio - Stand Alone Website |  | 01. Prod Discovery |  |  |  | BHJ |  | X | [7 empty] | Jan 2027 | Mar 2027 |  |  | 2026-09-07: Sumit; 2026-09-14: Sumit; 2026-09-21: Sumit
Jerel Smith | B2B | Increase B2B Acquisition |  | B2B Homepage About Us Module | BHP-7274 | 01. Prod Discovery |  |  |  | BHJ |  | X | [7 empty] | Feb 2027 | Feb 2027 |  | BHP-7274
| Used | Increase Trade In Awareness |  | Decouple Sell Used from Used Hub | BHP-7431 | 01. Prod Discovery |  |  |  | BHJ, BHIA, BIDW |  | X | X |  | X |  |  |  |  | Feb 2027 | Feb 2027 |  | BHP-7431
| Used | Increase Trade In Awareness |  | Sell Used Mega Menu | BHP-7430 | 01. Prod Discovery | [17 empty] | 2026-09-21: Sumit; 2026-09-28: Sumit
| Used | Improve Buy Used Customer Experience |  | Used Roll Up SKUs | BHP-6479 | 01. Prod Discovery | [13 empty] | Dec 2026 | Feb 2027
Jerel Smith | Used | Improve Trade In User Flow |  | Sell Used Purchase Look Up | BHP-7236 | 02. UX Req |  |  |  | BHJ, BHIA, SEARCH |  | X | X | [5 empty] | X | Nov 2026 | Jan 2027 |  | BHP-7236 | 2026-08-24: John; 2026-08-31: John; 2026-09-07: John
Jerel Smith | Used | Increase Trade In Awareness |  | Used Activity Notification | BHP-7237 | 02. UX Req | static |  |  | BHJ, UNIX, SEARCH |  | X |  | X |  |  |  |  | X | Dec 2026 | Jan 2027 |  | BHP-7237 | 2026-09-14: John; 2026-09-21: John; 2026-09-28: John
Jerel Smith | B2B | Improve The Studio B&H Customer Experience |  | The Studio - Enhanced Landing Page | BHP-6444 | 02. UX Req | b2bHub |  |  | BHJ, UNIX |  | X |  | X | [5 empty] | Jan 2027 | Jan 2027 |  | BHP-6444 | 2026-09-07: Sumit; 2026-09-14: Sumit; 2026-09-21: Sumit
Jerel Smith | Used | Increase Buy Used Awareness |  | Used Hub - Just Added Component | BHP-7229 | 02. UX Req |  |  |  | BHJ, BHIA |  | X | X | [6 empty] | Feb 2027 | Feb 2027 |  | BHP-7229 | 2026-08-10: John; 2026-09-07: John; 2026-09-14: John
Jerel Smith | Used | Increase Buy Used Awareness |  | Used Just Added Page | BHP-7230 | 02. UX Req |  |  |  | BIDW |  |  |  |  | X |  |  |  |  | Feb 2027 | Feb 2027 |  | BHP-7230 | 2026-05-18: Nachman; 2026-05-25: Nachman; 2026-10-05: Nachman; 2026-10-12: Nachman
Jerel Smith | Used | Increase Trade In Awareness |  | Increase Awareness of Trade In Offers - Best Buy Inspiration/Competitive Effort | BHP-6827 | 03. UX Discovery |  |  |  | BHJ, BHIA, SEARCH |  | X | X | [5 empty] | X | Oct 2026 | Oct 2026 |  | BHP-6827
Jerel Smith | Used | Increase Buy Used Awareness |  | Out of stock Alerts for used products | BHUX-35020 | 03. UX Discovery | productDetail |  |  | BHJ, BHIA, SEARCH |  | X | X | [5 empty] | X | Oct 2026 | Oct 2026 |  | BHP-4792 | 2026-08-03: Leo; 2026-08-10: Leo; 2026-08-17: Leo; 2026-08-24: Leo
Jerel Smith | B2B | Increase The Studio B&H Awareness |  | The Studio - B&H Awareness on High Ticket Items | BHUX-35304 | 03. UX Discovery | productDetail |  |  | BHJ |  | X | [7 empty] | Oct 2026 | Oct 2026 |  | BHP-7239 | 2026-08-17: Leo; 2026-08-24: Leo; 2026-08-31: Leo; 2026-09-07: Leo
Jerel Smith | Used | Increase Buy Used Awareness | Improve Discovery | Add New ¦ Used tab to all listing pages and search results pages | BHUX-35303 | 03. UX Discovery | productList |  |  | BHJ, BHIA |  | X | X | [6 empty] | Nov 2026 | Nov 2026 |  | BHP-5726 | 2026-08-24: Sumit; 2026-08-31: Sumit; 2026-09-07: Sumit; 2026-09-14: Sumit
Jerel Smith | B2B | Increase The Studio B&H Awareness |  | The Studio - Category Hybrid Page | BHP-7301 | 04. UX Design | productList |  |  | UNIX |  |  |  | X | [5 empty] | Oct 2026 | Oct 2026 |  | BHP-7301 | 2026-08-10: Sumit; 2026-08-24: Sumit; 2026-08-31: Sumit; 2026-09-07: Sumit
Jerel Smith | Find | Improve Discovery |  | Highlighted Refinements Enhancement | BHUX-35302 | 04. UX Design | productList | Filters |  | BHJ, BHIA, SEARCH |  | X | X | [5 empty] | X | Oct 2026 | Oct 2026 |  | BHP-7266 | 2026-08-24: Sumit; 2026-08-31: Sumit; 2026-09-07: Sumit; 2026-09-14: Sumit
Jerel Smith | Used | Improve Trade In User Flow |  | Trade In Email - Comprehensive Refresh Discovery | BHUX-34772 | 04. UX Design |  |  |  | BHJ |  | X | [7 empty] | Oct 2026 | Oct 2026 |  | BHP-6391 | 2026-07-13: John; 2026-07-20: John; 2026-07-27: John; 2026-08-03: John
Jerel Smith | Used | Improve Trade In User Flow |  | Used - Sell Used Experience | BHUX-33009 | 04. UX Design |  |  |  | BHJ |  | X | [7 empty] | Jan 2027 | Mar 2027 |  | BHP-6434 | 2026-04-20: John; 2026-04-27: John; 2026-05-04: John; 2026-05-11: John; 2026-05-18: John; 2026-05-25: John; 2026-06-01: John; 2026-06-08: John; 2026-06-15: John; 2026-06-22: John; 2026-06-29: John; 2026-07-06: John; 2026-07-13: John; 2026-07-20: John; 2026-07-27: John; 2026-08-03: John; 2026-08-10: John; 2026-08-17: John; 2026-08-24: John; 2026-08-31: John; 2026-09-07: John; 2026-09-14: John; 2026-09-21: John; 2026-09-28: John
Jerel Smith | Used | Increase Buy Used Awareness |  | Add 'shop by popular brands' section to Used Homepage | BHUX-34844 | 04. UX Design | category |  |  | BHJ |  | X | [7 empty] | Nov 2026 | Jan 2027 |  | BHP-6735 | 2026-07-20: John; 2026-07-27: John; 2026-08-03: John; 2026-08-10: John; 2026-08-17: John; 2026-08-24: John; 2026-08-31: John; 2026-09-07: John
Jerel Smith | Used | Increase Buy Used Awareness |  | Shop By Popular Brand' Listing Pages Discovery | BHUX-34845 | 04. UX Design | productList |  |  | BHJ |  | X | [7 empty] | Nov 2026 | Jan 2027 |  | BHP-6735 | 2026-07-27: Sumit; 2026-08-03: Sumit; 2026-08-10: Sumit; 2026-08-17: Sumit; 2026-08-24: Sumit; 2026-08-31: Sumit; 2026-09-07: Sumit
Jerel Smith | Used | Increase Buy Used Awareness |  | My Account > Trade In Awareness | BHUX-35010 | 04. UX Design | static | My Account Menu Item |  | BHJ, UNIX |  | X |  | X | [5 empty] | Dec 2026 | Dec 2026 |  | BHP-7196 | 2026-08-10: Mehek; 2026-08-17: Mehek; 2026-08-24: Mehek
Jerel Smith | B2B/Used | Increase Trade In Awareness | Increase B2B Acquisition | B2B & Used Visibility in the Nav | BHUX-34378 | 04. UX Design |  |  |  | BHJ, BHIA |  | X | X | [6 empty] | Feb 2027 | Feb 2027 |  | BHP-6900 | 2026-06-01: Sumit; 2026-06-08: Sumit; 2026-06-15: Sumit; 2026-06-22: Sumit; 2026-06-29: Sumit; 2026-07-06: Sumit; 2026-07-13: Sumit; 2026-07-20: Sumit; 2026-07-27: Sumit; 2026-08-03: Sumit; 2026-08-10: Sumit; 2026-08-17: Sumit; 2026-08-24: Sumit; 2026-08-31: Sumit; 2026-09-07: Sumit; 2026-09-14: Sumit; 2026-09-21: Sumit; 2026-09-28: Sumit
Jerel Smith | Used | Improve Trade In User Flow |  | Sell Used User Flow Design Validation | BHUR-133 | 04A. Research - Design Validation |  |  |  | BHJ |  | X | [10 empty] | BHP-6434 | 2026-07-06: Hanna; 2026-07-13: Hanna; 2026-07-20: Hanna; 2026-07-27: Hanna; 2026-08-03: Hanna; 2026-08-10: Hanna; 2026-08-17: Hanna; 2026-08-24: Hanna; 2026-08-31: Hanna; 2026-09-07: Hanna
Jerel Smith | Used | Improve Trade In User Flow |  | Used Status Email Update | BHUX-34723 | 06. Architecture |  |  |  | BHJ, UNIX |  | X |  | X | [5 empty] | Oct 2026 | Oct 2026 |  | BHP-7145 | 2026-07-13: John
Jerel Smith | Used | Increase Trade In Awareness |  | PDP Purchased in 20XX, Trade In Value is $YYY.YY | BHUX-35309 | 06. Architecture | productDetail |  |  | BHJ |  | X | [7 empty] | Oct 2026 | Oct 2026 |  | BHP-7228 | 2026-08-17: Alice
Jerel Smith | B2B | Increase B2B Acquisition |  | B2B Hub Landing Page - redesign | BHUX-26541 | 07. Grooming | b2bHub |  |  | BHJ |  | X | [7 empty] | Oct 2026 | Dec 2026 |  |  | 2026-04-13: Jaye; 2026-04-20: Jaye; 2026-04-27: Jaye; 2026-05-04: Jaye; 2026-05-11: Jaye
Jerel Smith | B2B | Increase B2B Acquisition |  | B2B Hub - Revisit Signup Flow | BHUX-31874 | 07. Grooming | b2bHub |  |  | BHJ |  | X | [7 empty] | Oct 2026 | Dec 2026 |  |  | 2026-04-13: Jaye; 2026-04-20: Jaye; 2026-04-27: Jaye; 2026-05-04: Jaye; 2026-05-11: Jaye; 2026-05-18: Jaye; 2026-05-25: Jaye
Jerel Smith | B2B | Increase B2B Acquisition |  | B2B Hub Redesign - Internal Pages | BHUX-32257 | 07. Grooming | b2bHub | [12 empty] | Oct 2026 | Dec 2026 |  |  | 2026-04-20: Jaye; 2026-04-27: Jaye; 2026-05-04: Jaye; 2026-05-11: Jaye
Jerel Smith | Find | Improve Discovery |  | Nested Refinements | BHUX-32621 | 08. Ready for Dev | productList | Filters | [11 empty] | Oct 2026 | Oct 2026 |  | BHP-2802
Jerel Smith | Find | Improve Discovery |  | Mega Menu | BHUX-29580 | 09. In Dev |  | Top Nav |  | BHJ, BHIA, BIDW |  | X | X |  | X |  |  |  |  | Sep 2026 | Sep 2026 |  | BHUX-29580 | 2026-04-27: Laura; 2026-05-04: Laura; 2026-06-01: Sumit
Jerel Smith | B2B | Increase B2B Acquisition |  | School Safety Landing Page | BHUX-34377 | 09. In Dev |  |  |  | BHJ |  | X | [7 empty] | Sep 2026 | Sep 2026 |  | BHP-5830 | 2026-06-15: Hilli; 2026-06-22: Hilli; 2026-06-29: Hilli; 2026-07-06: Hilli; 2026-07-13: Hilli; 2026-07-20: Hilli; 2026-07-27: Hilli; 2026-08-03: Hilli; 2026-08-10: Hilli
Jerel Smith | Find | Improve Discovery |  | Sunset Modals for Drawers | BHUX-32543 | 09. In Dev | productList | [12 empty] | Aug 2026 | Aug 2026 |  | BHP-6228
Jerel Smith | Used | Improve Trade In User Flow |  | Trade In Discrepancy Email Refresh (Copy Only) |  | 09. In Dev | [13 empty] | Sep 2026 | Sep 2026 |  |  | 2026-07-13: John; 2026-07-20: John
Jerel Smith | Used | Increase Buy Used Awareness |  | Condition Grouping | BHUX-33519 | 13. Live |  |  |  | BHUX, BHJ | X | X | [7 empty] | Aug 2026 | Aug 2026 |  | BHP-4518 | 2026-04-27: Leo; 2026-05-04: Leo
| Find | Improve Discovery |  | Sliders | BHUX-17615 | 13. Live | productList |  |  | BHUX, BHJ | X | X | [10 empty] | BHP-3757
| Find | Improve Discovery |  | Refinement - Select All/Deselect All | BHUX-23755 | 13. Live | productList |  |  | BHUX, BHJ | X | X | [10 empty] | BHP-2638
| Find | Improve Discovery |  | My Gear 2 - Tray | BHUX-28124 | 13. Live |  |  |  | BHUX, BHJ | X | X | [10 empty] | BHP-5060
| Find | Improve Discovery |  | H2 on listing pages | BHUX-31245 | 13. Live | productList |  |  | BHUX, BHJ | X | X | [10 empty] | MRCH-2202
| Find | Improve Discovery |  | Sunset Dealzone | BHUX-32071 | 13. Live | productList |  |  | BHUX, BHJ | X | X | [10 empty] | BHJ-119850
| Find | Improve Discovery |  | Highlighted Refinements | BHUX-29921 | 13. Live | productList |  |  | BHUX, BHJ, BHIA | X | X | X | [9 empty] | BHP-5132
Jerel Smith | B2B | Increase B2B Acquisition |  | EDU Homepage | BHUX-25601 | 13. Live |  |  |  | BHUX, BHJ | X | X | [7 empty] | Aug 2026 | Aug 2026 |  | BHP-3583 | 2026-05-04: Hilli; 2026-06-15: Hilli
| Used | Improve Buy Used Customer Experience |  | Actual Used Images | BHP-4563 | 13. Live | [16 empty] | BHP-4563
| Used | Increase Buy Used Awareness |  | Used Hub Enhancements | BHUX-31354 | 13. Live | category |  |  | BHUX, BHJ | X | X | [10 empty] | BHP-5817

## Model (Don't Touch) (hidden)
Reduce impediments and increase transparency/trust across internal teams by answering the following questions:
Who wants this?
Why are we doing this?
What's the bigger picture?
How do we know if it worked?
Where will the customer encounter this experience?
Portfolios | Who are the primary stakeholders?
Theme | What are the ongoing high level efforts that create a positive impact on customer experience and revenue?
Theme | What is the sequence of deliverables and why?
Metrics | Through which lens do we judge performance/success?
Components | What elements are involved in this theme/request?
GA4 | Is the Component tagged? If so, is it tagged in a meaningful way?

## Obsolete (hidden)
Product | Portfolio | Theme | Title | Jira | Status
Brendan Bagley |  |  | Tax & Net 30 Terms On CompanyID | BHUX-33524 | 06. Architecutre
Brendan Bagley | B2B |  | B2B Updated Expired Tax Exemption | BHUX-33186 | 05. Business Review
Brendan Bagley | Site Support |  | Enable Editable Email Addresses in the ShipTo | BHUX-34079 | 05. Business Review
Brendan Bagley | B2B Portals |  | Identify Users via the PunchoutSetupRequest and Give them Limited User-Based Features | BHUX-33409 | 05. Business Review
Brendan Bagley | B2B |  | Update Punch out Cart to match B2B/B2B cart/checkout | BHUX-33526 | 05. Business Review
Brendan Bagley | B2B |  | Gradus equivalents in B2B Quotes | BHUX-33797 | Closed as later

## Control
Portfolio | Status | Theme | Description | Measure Adoption | Measure Impact | Event Taxonomy | Sprint | Tech Resource | Page Type | Component (GA4)
B2B | 00. Parking Lot | Improve Discovery | OG Find initaitives that Jerel still owns | Refinement usage rate, Search-to-listing CTR, Mega menu / nav click through rate, Sessions using two or more filters | Listing-to-PDP rate, Zero-result search rate, Search-attributed conversion rate, Time to first PDP view |  |  | BHUX | category | Add to Compare
Used | 01A. Research - Foundational | Increase Trade In Awareness | Surface trade-in as a clear, relevant option at high-intent moments, Order History, PDPs, post-purchase, so customers who own eligible gear know they can trade it in. | Trade-in CTA Impressions (Order History/PDP), CTA Click through rate, % of eligible sessions exposed to CTA | New to trade in quote starts, Quote start rate among CTA exposed users, Assisted trade-in revenue (CTA attributed) | listing_page_clicks | Jan 2026 | BHJ | home | Breadcrumb
Find | 01. Prod Discovery | Improve Trade In User Flow | Reduce friction in the sell/trade-in submission flow: search, quote, shipping/drop-off, to raise completion and quote-to-conversion rates. | % started quotes completed, Time to quote (median), Post-acceptance ststus engagement rate | Quote-to-accepted-offer rate, Drop-off rate by flow step, sell-flow CSAT (isolated), Support contact rate per quote, Payout cycle time (accepted>paid) | category_page_clicks | Feb 2026 | BHIA | productDetail | Category Banner
| 02. UX Req | Increase Trade In Reactivation | Re-engage past customers with unused eligible gear via triggered emails tied to purchase timing and inventory demand signals. | Reactivation email open rate, reactivation email CTR, quote starts attributed to email | Reactivated quote to completion rate, revenue from reactivated sellers, days since last purchase > trade in (trend) | detail_page_clicks | Mar 2026 | UNIX | productList | Category Groups
| 03. UX Discovery | Increase Buy Used Awareness | Grow discovery of the Used Hub and used inventory through SEO, brand listing pages, and internal linking so more shoppers know B&H sells used gear. | Organic sessions to Used Hub/brand pages, Search impressions & CTR (used pages), Internal link CTR (New>used cross links), Cross-sell CTA impressions (used alt. on New PDP) | New-to-used buyer sessions, Used PDP views per session, Used share to total category traffic, cross sell attributed used PDP views/purchases | header_clicks | Apr 2026 | BIDW | b2bHub | Explora banner
| 04. UX Design | Improve Buy Used Customer Experience | Make used PDPs and listing pages easier to evaluate, increase condition clarity, provide product photos, and filtering, so shoppers can confidently purchase used gear | PLP filter usage rate, used pdp engagement rate (photo/spec expansion), order status page engagement rate | Used PDP-to-cart rate, Used cart-to-purchase rate, Post-Purchase CSAT (isolated) | mega_menu_clicks | May 2026 | BHUR | static | Filter Labels
| 04A. Research - Design Validation | Increase Buy Used Reactivation | Win back past buyers with relevant used-inventory alerts and win-back offers matched to their purchase history | Win Back email open rate, win-back email CTR, Browse to used PDP rate from email | Repeat used-purchase rate, Revenue from reactivated buyers, Time-since-last-purchase > repurchase (trend) | typeahead_suggestion_clicks | Jun 2026 | DBA |  | Filters
| 05. Business Review | Increase B2B Acquisition | Grow the pipeline of registered B2B accounts by making the B2B Hub, EDU and vertical landing pages easier to find and sign up from, so qualifying organisations self-serve rather than routing through sales. | Sessions to B2B Hub / EDU / vertical landing pages, Sign-up form starts, Sign-up CTA click through rate, % of B2B sessions reaching a landing page | Completed B2B registrations, Registration-to-first-order rate, New B2B accounts per month, Revenue from newly registered accounts | footer_clicks | Jul 2026 | WEBC |  | Item List
| 06. Architecture | Increase The Studio B&H Awareness | Build awareness that The Studio is a B&H offering by surfacing B&H branding and cross-links on high-ticket products and Studio entry points, so customers connect the two. | Sessions to Studio landing and category pages, B&H awareness module impressions on high-ticket PDPs, Cross-link click through rate, Organic impressions for Studio terms | New-to-Studio sessions, Studio PDP views per session, Studio share of high-ticket category traffic, Assisted Studio revenue | home_page_clicks | Aug 2026 | SEARCH |  | Listing See All Info
| 07. Grooming | Improve The Studio B&H Customer Experience | Make Studio category, landing and hybrid pages easier to evaluate and navigate, so customers can compare and specify Studio products without leaving for a sales conversation. | Studio category page engagement rate, Hybrid page filter usage, Spec / detail expansion rate, Quote or enquiry form starts | Studio PDP-to-cart rate, Enquiry-to-quote rate, Studio CSAT (isolated), Support contact rate per Studio session | nav_drawer_clicks | Sep 2026 |  |  | Listing See All Modal
| 08. Ready for Dev | Increase Trust & Condition Transparency | Cross-cutting theme covering whether customers believe the grading/condition information is accurate and complete, ties directly to condition rating scale and PDP condition grouping work, and carries COO-level visibility | Condition information expansion rate on used PDPs, Actual-image gallery engagement rate, Condition rating scale page views, Filter usage by condition | Used PDP-to-cart rate by condition, Condition-related return rate, Condition-related support contacts per order, Post-purchase CSAT on condition accuracy | cart_page_clicks | Oct 2026 |  |  | Other Buying Options
| 09. In Dev | Improve Search & Findability | Cross-cutting theme spanning sell-side item search (finding what you own to quote it) and buy-side discovery (finding used inventory to purchase). Flagged as the single highest-priority friction point across VoC research on both sides. | Search usage rate (sell and buy side), Refinement usage per search, Typeahead selection rate, Searches per session | Zero-result search rate, Search-to-PDP rate, Search-attributed quote starts (sell side), Search-attributed used purchases (buy side) | checkout_page_clicks | Nov 2026 |  |  | Paging
| 10. QA |  |  |  |  | checkout_impression | Dec 2026 |  |  | Pro Audio menu
| 11. UAT |  |  |  |  | login_layer_clicks | Jan 2027 |  |  | SEO Text
| 12. Release |  |  |  |  | profile_menu_clicks | Feb 2027 |  |  | Search
| 13. Live |  |  |  |  | my_account_clicks | Mar 2027 |  |  | Show More
[6 empty] | order_history_detail_clicks | Apr 2027 |  |  | Sort By
[6 empty] | modify_order_page_clicks | May 2027 |  |  | Tab Navigation
[6 empty] | static_pages_clicks | Jun 2027 |  |  | Top Nav
[6 empty] | gift_ideas_clicks | Jul 2027 |  |  | Trade In - Learn More
[6 empty] | leasing_page_clicks | Aug 2027 |  |  | Trade in Your Gear
[6 empty] | payboo_page_clicks | Sep 2027 |  |  | Typeahead Suggestions
[6 empty] | payboo_sdk_clicks | Oct 2027 |  |  | Used Item Condition
[7 empty] | Nov 2027 |  |  | View
[7 empty] | Dec 2027 |  |  | chatBanner
searchDropdown
My Account Menu Item

## Metrics
Portfolio | Theme | Metric | Description | Calculation | Why it Matters | Type | Source | Components | Available
Used | Increase Trade In Awareness | Trade-in CTA Impressions (Order History/PDP) | The number of times a trade-in call-to-action (button, banner, or module) was actually rendered and seen through out the site. | Count of CTA element view events, deduped per session. | Impressions are the ceiling on everything downstream. If the CTA isn't being shown, nothing else in this theme can move. | Adoption | GA4 | Homepage Banner, PDP, PLP, My Account
Used | Increase Trade In Awareness | CTA Click through rate | Of the sessions where the CTA was shown, the share that clicked it. | CTA clicks ÷ CTA impressions. | Tells you whether the CTA itself (copy, placement, design) is compelling, independent of how often it's shown. | Adoption | GA4 | Homepage Banner, PDP, PLP, My Account
Used | Increase Trade In Awareness | % of eligible sessions exposed to CTA | Of all sessions where a customer has an eligible order/product (i.e. the CTA logic should have fired), the share that actually saw it. | Sessions with CTA impression ÷ sessions meeting eligibility criteria. | Separates "the CTA doesn't work well" from "the CTA isn't reaching who it should," a targeting/eligibility-logic health check. | Adoption | GA4 | Homepage Banner, PDP, PLP, My Account
Used | Increase Trade In Awareness | New to trade in quote starts | Quote submissions started by customers who have never started a trade-in quote before. | Count of first-ever quote-start events, matched against customer history in the Quote system. | Isolates net-new acquisition from repeat sellers, so the awareness theme is measured on bringing in new sellers, not just repeat activity. | Impact | Quote system | Sell Used Search, My Account Trade In Module, Trade In Page
Used | Increase Trade In Awareness | Quote start rate among CTA exposed users | Of customers exposed to the trade-in CTA, the share who went on to start a quote (not necessarily via the CTA itself, any path). | Quote starts among CTA-exposed users ÷ CTA-exposed users. | The real end-to-end conversion signal for the awareness surface, closer to business outcome than CTR alone. | Impact | GA4 + Quote system
Used | Increase Trade In Awareness | Assisted trade-in revenue (CTA attributed) | Dollar value of inventory acquired through trade-ins where the CTA played a role in the customer's path, even if not the last touch before quoting. | Sum of accepted-quote $ value for quotes with a CTA touchpoint anywhere in the session/journey. | Awareness surfaces often assist rather than directly convert. Last-touch attribution alone would undercount their value. | Impact | GA4 + Finance | Homepage Banner, PDP, PLP, My Account
Used | Increase Trade In Awareness | Cross-sell CTA impressions (New PDP / brand pages) | Impressions of a trade-in prompt shown while a customer is browsing new (not used) gear, e.g. "have an old one? trade it in." | Count of CTA view events on New PDP / brand pages, deduped per session. | This is a different acquisition channel than Order History awareness. It reaches people who haven't bought from B&H recently. | Adoption | GA4 | New PDP Trade In Your Gear
Used | Increase Trade In Awareness | Cross-sell-attributed quote starts | Quote starts that can be traced back to the cross-sell CTA shown on New PDP/brand pages. | Quote-start events with a cross-sell CTA touchpoint in the preceding session(s). | Tests whether pulling people out of the New funnel into trade-in actually works as an acquisition channel, distinct from Order History awareness. | Impact | GA4 + Quote system | New PDP Trade In Your Gear
Used | Improve Trade In User Flow | % started quotes completed | Of all quote flows a customer started (searched/selected at least one item), the share that reached a final submitted quote. | Completed quote submissions ÷ quote flows started. | The single clearest signal of overall flow friction, the headline number for this theme. | Adoption | Quote system
Used | Improve Trade In User Flow | Time to quote (median) | How long it takes a customer to go from starting the flow to receiving a quote value, at the midpoint of the distribution. | Median of (quote-received timestamp − flow-start timestamp) across completed quotes. | Slow quoting is a known drop-off driver; median avoids a few slow outliers skewing the picture. | Adoption | Quote system
Used | Improve Trade In User Flow | Post-acceptance status engagement rate | Of customers who accepted a quote, the share who opened a status update (email or status page) about shipping/payout progress. | Unique opens/views of post-acceptance status content ÷ accepted quotes. | Checks whether status communications meant to reduce post-acceptance uncertainty are actually being read. | Adoption | ESP + GA4 | Email Shipping Email, Trade in Quote Notification
Used | Improve Trade In User Flow | Quote-to-accepted-offer rate | Of quotes issued to customers, the share the customer actually accepted. | Accepted quotes ÷ quotes issued. | Distinguishes "the flow works but the price is wrong" (low acceptance) from "the flow itself is broken" (low completion, above). | Impact | Quote system | Email CTA
Used | Improve Trade In User Flow | Drop-off rate by flow step | The percentage of customers who exit at each individual step of the sell flow (e.g. item search, condition selection, shipping info). | (Users entering step − users entering next step) ÷ users entering step, per step. | Pinpoints exactly where in the flow friction is worst, so fixes can be targeted rather than guessed at. | Impact | GA4 | Sell Used Search Box, Sell Used Type Ahead, Sell Used Listing Page, Sell Used Detail Page, Sell Used Review Page
Used | Improve Trade In User Flow | Sell-flow CSAT (isolated) | Customer satisfaction score from a survey specifically scoped to the sell/trade-in flow, kept separate from site-wide CSAT. | Medallia CSAT question average/top-box %, filtered to sell-flow survey instance. | Site-wide CSAT would dilute sell-flow-specific pain; isolating it makes the score actionable for this theme. | Impact | Medallia
Used | Improve Trade In User Flow | Support contact rate per quote | How often a customer contacts support (chat, phone, email) in connection with a given quote. | Support tickets tagged to a quote ID ÷ total quotes. | A proxy for hidden friction. High contact rates mean customers can't self-serve through confusion or problems in the flow. | Impact | Support / CRM
Used | Improve Trade In User Flow | Payout cycle time (accepted>paid) | Time elapsed from a customer accepting a quote to the payout actually being issued. | Payout-issued timestamp − quote-accepted timestamp, median across accepted quotes. | Payout speed is a top driver of seller trust and repeat behavior. | Impact | Finance + WMS
Used | Increase Trade In Reactivation | Reactivation email open rate | Share of sent trade-in reactivation emails that were opened. | Unique opens ÷ emails delivered. | The first checkpoint. If subject lines/targeting aren't landing, nothing downstream can work. | Adoption | ESP | Trade in email
Used | Increase Trade In Reactivation | Reactivation email CTR | Share of sent reactivation emails that resulted in a click. | Unique clicks ÷ emails delivered (or ÷ opens, for click-to-open rate). | Tests whether the email content/offer itself is compelling once someone opens it. | Adoption | ESP | Used Email, Used Email CTA
Used | Increase Trade In Reactivation | Quote starts attributed to email | Quote flows started by a customer within a defined attribution window after clicking a reactivation email. | Quote-start events with a reactivation-email click in the prior N days (window TBD). | Bridges "they clicked" to "they actually engaged with the trade-in flow." | Adoption | ESP + Quote system
Used | Increase Trade In Reactivation | Reactivated quote to completion rate | Of quotes started via reactivation email, the share that reach a completed/accepted quote. | Completed quotes (email-attributed) ÷ quote starts (email-attributed). | Checks whether reactivated sellers behave differently than new/organic sellers once in the flow. | Impact | Quote system
Used | Increase Trade In Reactivation | Revenue from reactivated sellers | Total $ value of inventory acquired from customers reactivated via this campaign. | Sum of accepted-quote $ value for email-attributed reactivated sellers. | The bottom-line business case for continuing to invest in reactivation campaigns. | Impact | Finance + Quote system
Used | Increase Trade In Reactivation | Days since last purchase > trade in (trend) | How long, on average, it takes a past purchaser to trade in gear after their last purchase, tracked as a trend over time. | Trade-in date − most recent prior purchase date, averaged/median across reactivated sellers, tracked quarter over quarter. | If this trend is shortening, it suggests the timing/targeting logic behind the campaign triggers is improving. | Impact | CRM
Used | Increase Buy Used Awareness | Organic sessions to Used Hub/brand pages | Sessions landing on Used Hub or used brand listing pages via unpaid search. | GA4 sessions filtered to organic-search channel + landing page = Used Hub/brand pages. | The core SEO health signal for the whole awareness theme, a direct read on whether the hybrid listing-page architecture is working. | Adoption | GA4 | Used Hub, Used Brand Listing Page
Used | Increase Buy Used Awareness | Search impressions & CTR (used pages) | How often used pages show up in Google search results, and what share of those impressions turn into a click. | Pulled directly from Google Search Console, filtered to used-page URLs. | A leading indicator ahead of organic sessions, showing whether pages are being surfaced/ranked before traffic shows up. | Adoption | Google Search Console
Used | Increase Buy Used Awareness | Internal link CTR (New>used cross links) | Click-through rate on links that point from new-gear pages (e.g. brand pages owned by Sammy) into used inventory. | Clicks on internal used-links ÷ impressions of those links. | Internal linking is both an SEO signal and a direct discovery channel. This checks it's actually being used. | Adoption | GA4 | New PDP, Used PDP
Used | Increase Buy Used Awareness | Cross-sell CTA impressions (used alt. on New PDP) | Impressions of a "used alternative available" prompt shown on a new-gear product page. | Count of CTA view events on New PDPs, deduped per session. | Catches price-sensitive shoppers already in a New PDP session, a distinct discovery channel from search/SEO. | Adoption | GA4
Used | Increase Buy Used Awareness | New-to-used buyer sessions | Sessions from customers who have never viewed or purchased a used product before. | Sessions with a used PDP view, matched against customer history for first-time-used flag. | Awareness should be judged on growing the used buyer base, not just increasing traffic from existing used shoppers. | Impact | GA4
Used | Increase Buy Used Awareness | Used PDP views per session | Average number of used product pages viewed within a single session. | Total used PDP views ÷ total sessions with at least one used PDP view. | A rough proxy for browsing depth/engagement once a shopper lands in the used ecosystem. | Impact | GA4
Used | Increase Buy Used Awareness | Used share to total category traffic | Used PDP/category traffic as a percentage of all traffic (new + used) to the same product categories. | Used-category sessions ÷ (used + new-category sessions), by category. | Shows whether used is growing its footprint relative to new, not just growing alongside site-wide traffic. | Impact | GA4 | Used PDP, Used Category Landing Page, Used Category Listing Page, New PDP, New Category Landing Page, New Category Listing Page
Used | Increase Buy Used Awareness | Cross sell attributed used PDP views/purchases | Used PDP views or purchases that followed a cross-sell CTA click on a New PDP. | Used PDP views/purchases with a cross-sell CTA touchpoint in the preceding session(s). | Validates whether the New→Used cross-sell mechanism is actually converting, not just generating impressions. | Impact | GA4 | Used PDP, Used Check Out?, New Product Card Used From
Used | Improve Buy Used Customer Experience | PLP filter usage rate | Share of used listing-page sessions where a customer applies at least one filter (price, brand, condition, etc.). | Sessions with a filter-applied event ÷ used PLP sessions. | Low usage can mean filters aren't helpful/discoverable; high usage with low downstream conversion can flag a filter/inventory mismatch. | Adoption | GA4 | Used PLP, Used SRP, Used Filter
Used | Improve Buy Used Customer Experience | Used PDP engagement rate (photo/spec expansion) | Share of used PDP sessions where a customer interacts with photos (zoom/gallery) or expands spec/condition detail sections. | Sessions with photo-interaction or spec-expansion events ÷ used PDP sessions. | A proxy for how much evaluation effort shoppers are putting in, tied directly to the photography and condition-clarity investments underway. | Adoption | GA4
Used | Improve Buy Used Customer Experience | Order status page engagement rate | Share of used-order customers who view their order status page after purchase. | Unique order-status-page views ÷ used orders placed. | Post-purchase visibility affects trust and support load, mirroring the post-acceptance metric on the sell side. | Adoption | GA4 | My Orders
Used | Improve Buy Used Customer Experience | Used PDP-to-cart rate | Share of used PDP sessions that result in an add-to-cart. | Add-to-cart events on used PDPs ÷ used PDP sessions. | The core "does the PDP convince the shopper" metric, most sensitive to condition clarity and photography quality. | Impact | GA4 | Used PDP, Used PDP CTA
Used | Improve Buy Used Customer Experience | Used cart-to-purchase rate | Share of used add-to-cart events that result in a completed purchase. | Used purchases ÷ used add-to-cart events. | Isolates checkout-stage friction from PDP-stage persuasion, since the two have different fixes. | Impact | GA4 | Used PDP, Used PDP CTA, Used PLP, Used PLP CTA
Used | Improve Buy Used Customer Experience | Post-Purchase CSAT (isolated) | Customer satisfaction score from a survey scoped specifically to the used buying experience after delivery. | Medallia CSAT average/top-box %, filtered to used post-purchase survey instance. | Captures whether the product matched expectations set on the PDP, the buy-side counterpart to sell-flow CSAT. | Impact | Medallia | Medallia Survey
Used | Increase Buy Used Reactivation | Win-Back email open rate | Share of sent win-back emails that were opened. | Unique opens ÷ emails delivered. | Same logic as trade-in reactivation, the entry checkpoint for the whole campaign. | Adoption | ESP
Used | Increase Buy Used Reactivation | Win-back email CTR | Share of sent win-back emails that resulted in a click. | Unique clicks ÷ emails delivered (or ÷ opens for click-to-open). | Tests whether the specific inventory/offer surfaced in the email is relevant enough to act on. | Adoption | ESP | Email CTA
Used | Increase Buy Used Reactivation | Browse to used PDP rate from email | Of customers who clicked into the site from a win-back email, the share who viewed a used PDP during that session. | Sessions with used PDP view ÷ sessions originating from win-back email click. | Confirms the email is routing people to relevant used inventory, not just generic site traffic. | Adoption | GA4 + ESP | Email CTA, Used PDP
Used | Increase Buy Used Reactivation | Repeat used-purchase rate | Of past used buyers targeted by win-back campaigns, the share who complete another used purchase. | Repeat used purchases (email-attributed) ÷ past used buyers targeted. | The core outcome metric for this theme: did the campaign actually bring buyers back. | Impact | Order system
Used | Increase Buy Used Reactivation | Revenue from reactivated buyers | Total $ revenue from purchases made by win-back-campaign-attributed customers. | Sum of order value for email-attributed repeat purchases. | The bottom-line business case, mirroring "Revenue from reactivated sellers" on the sell side. | Impact | Finance + Order system
Used | Increase Buy Used Reactivation | Time-since-last-purchase > repurchase (trend) | How long, on average, it takes a past buyer to make another used purchase after being targeted, tracked as a trend over time. | Repurchase date − most recent prior purchase date, averaged/median, tracked quarter over quarter. | A shortening trend suggests campaign timing/targeting is getting more effective at catching buyers when they're ready. | Impact | CRM
Used | Search & Findability | Sell-item search success rate (Solr) | Share of sell-flow item searches where the customer found and selected their item (vs. abandoning or falling back to manual entry). | Searches ending in item selection ÷ total sell-flow searches. | Search friction is the #1 flagged issue in VoC research for the sell side specifically. This is the direct health check on it. | Adoption | Solr logs | Sell Used Search Box, Sell Used Type Ahead, Sell Used Listing Page
Used | Search & Findability | Used PLP/search zero-result rate | Share of used-inventory searches that return no results. | Zero-result searches ÷ total used-inventory searches. | A hard failure signal. Every zero-result search is a shopper who couldn't find anything, regardless of whether inventory actually existed. | Adoption | Solr logs | Site Search, Used Site Search
Used | Search & Findability | Used search-to-click rate | Share of used-inventory searches where the customer clicked a result. | Searches with a result click ÷ total used-inventory searches. | Distinguishes "no results" failures from "results shown but not relevant/appealing" failures. | Adoption | GA4 | Site Search, Used Site Search, Used Product Card
Used | Search & Findability | Search-originated quote starts (sell side) | Quote starts that began with a successful sell-flow search. | Quote starts preceded by a search-with-selection event. | Connects search quality directly to the acquisition funnel, not just to search-specific metrics. | Impact | Solr logs + Quote system | Sell Used Serach
Used | Search & Findability | Search-originated used purchases (buy side) | Used purchases that began with a used-inventory search (as opposed to browsing/category navigation). | Purchases preceded by a used search-with-click event in the same session. | Shows how much revenue depends on search working well, making the business case for search investment concrete. | Impact | GA4 | Site Search, Used Site Search
Used | Search & Findability | Search abandonment rate | Share of search sessions (sell or buy) where the customer leaves the site shortly after searching, without further engagement. | Sessions ending within N actions of a search event ÷ total search sessions. | The most direct "we lost them" signal. A search that doesn't even get a follow-up click or scroll is a clear failure. | Impact | GA4 + Solr logs | Site Search, Used Site Search, Sell Used Search
Used | Trust & Condition Transparency | Condition-tab view rate | Share of used PDP sessions where the customer opens/expands the condition detail tab or section. | Sessions with condition-tab-expand event ÷ used PDP sessions. | Shows how much shoppers are actively seeking out condition information, the core evaluation input for a used purchase. | Adoption | GA4 | PDP Condition Rating Link, PDP Condition Rating Tray
Used | Trust & Condition Transparency | Condition rating comprehension (usability test pass rate) | In moderated or unmoderated usability testing, the share of participants who correctly interpret what a given condition rating (e.g. "Good," "Excellent") means for the product they're evaluating. | Correct interpretations ÷ total test participants, per study. | Adoption metrics from analytics can't tell you if customers actually understand the rating scale. This is the qualitative check that they do, tied directly to the new five-tier scale rollout. | Adoption | Research / usability testing
Used | Trust & Condition Transparency | "Not as described" return rate | Share of used-order returns where the customer's stated reason is that the item didn't match its condition description. | Returns coded "not as described" ÷ total used orders. | The clearest hard evidence of a trust failure. A rising rate means the condition info shown isn't matching what customers receive. | Impact | Returns / CRM
Used | Trust & Condition Transparency | Medallia condition-satisfaction / trust score | Survey-based score measuring how satisfied/confident customers felt about the accuracy of condition information before and after receiving their item. | Medallia average/top-box % on the condition-trust survey question(s). | A softer, earlier-warning companion to the return-rate metric, capturing dissatisfaction even among customers who keep the item. | Impact | Medallia
Used | Trust & Condition Transparency | Grading accuracy / consistency (QA re-grade audit) | How often an independent re-grade of a sampled item matches the original evaluator's condition grade. | Re-grades matching original grade ÷ total items re-graded in the audit sample. | Traces trust problems back to their root cause, inaccurate grading upstream, rather than just a PDP/description-clarity issue. | Impact | DES eval + QA audit

## GA4
Product_Type | Element | component type | eventName | component_GA4 | label | label_value | site_type | page_type | Trigger & Other Parameters | Flag
N/A |  | Page Load | page_view | — | — | — | Desktop | productList | Initial render and every filter/sort/paging change (pushState)content_group: productList · site_langauge: E · bi: NoValue · pwa_source: NoValue · bh_user_id · category_page_id: 9811 | observed
N/A |  | Page Load | view_item_list | — | — | — | Desktop | productList | Results grid rendered — 28 items in one senditems[]: item_id, item_code, item_list_name, index, sales_comment · position_index: 1 | observed
N/A |  | Page Load | view_item_list | — | — | — | absent | absent | Google Ads remarketing duplicate — separate send, not the GA4 propertysend_to: google_ads · ecomm_pagetype: productList · ecomm_prodid[] · tag: AW-1056059933 | by design
N/A |  | Page Load | view_promotion | — | — | — | Desktop | productList | Hero banner impression — the Nikon trade-in unitcreative_name: IO Image Banner · creative_slot: HERO · promotion_name: 3385025 - BHUX 35089 Nikon Z6III Listing Page · promotion_url: /a/trade-in/64435 | observed
N/A |  | Page Load | view_promotion | — | — | — | Desktop | productList | Sponsored carousel — one event per slotcreative_name: spotfront list item · creative_slot: TOP · promotion_position: 1, 2, 3 · promotion_id (uuid) · promotion_url | observed
N/A |  | Page Load | view_promotion | — | — | — | Desktop | productList | Email slide-out and mega-menu banner impressionscreative_name: Email Slideout Signup / IO Banner · creative_slot: SLIDER / Top Nav · promotion_id: ESS | observed
New | Homepage Banner | Banner | select_promotion
New | Top Nav | Navigation | mega_menu_clicks | Top Nav | Computers | — | Desktop | category
New | New Mega Menu | Navigation - Mega Menu | mega_menu_clicks | Pro Audio menu | Live sound | —
New | New Site Search Box | Search | header_clicks | Search | Enter Search |  | Desktop | home
New | New Site Search Type Ahead | Search | typeahead_suggestion_clicks | Typeahead Suggestions | — | — | — | —
New | New Item Category Listing Page | PLP |  |  |  |  | Desktop | productList
New | New Item Category Listing Page Product Card Used From CTA | CTA |  |  |  |  | Desktop | productList
N/A | New Item Category Listing Page | Refinements | listing_page_clicks | Filters | — | — | Desktop | productList | Left-rail facet checkboxfilter_value: Full Frame (35mm) · filter_section: Sensor Size · filter_n_value: fct_sensor-size_3087 · from: left refinements | observed
N/A | New Item Category Listing Page | Refinements | listing_page_clicks | Filters | — | — | Desktop | productList | Left-rail Categories link (Mirrorless Cameras)filter_value: "undefined" · filter_section: Category · filter_n_value: Mirrorless Cameras · from: "undefined" | F1
N/A | New Item Category Listing Page | Refinements | listing_page_clicks | Filter Labels | Still Image Resolution | — | Desktop | productList | Facet accordion expand/collapse — label carries the section name | observed
N/A | New Item Category Listing Page | Refinements | listing_page_clicks | Listing See All Info | left refinements | — | Desktop | productList | "See all + 10" opens the full-facet modal — label carries placement, not which facet | F3
N/A | New Item Category Listing Page | Refinements | listing_page_clicks | Listing See All Modal | Clear All | — | Desktop | productList | Clear All inside the modal — the only modal control that emits anything | F2
N/A | New Item Category Listing Page | Listing Controls | listing_page_clicks | Sort By | "" (empty) | — | Desktop | productList | Opening the sort dropdown — fires with an empty label before any choice is made | F4
N/A | New Item Category Listing Page | Listing Controls | listing_page_clicks | Sort By | PRICE_LOW_TO_HIGH | — | Desktop | productList | Sort selected — label is the enum, not the visible "Price: Low to High" | observed
N/A | New Item Category Listing Page | Listing Controls | listing_page_clicks | View | Grid View · List View | — | Desktop | productList | Grid/list density toggle | observed
N/A | New Item Category Listing Page | Listing Controls | listing_page_clicks | Paging | page 2 | — | Desktop | productList | Pagination control — label is the literal "page " prefix plus the number | observed
New |  | Product Title | select_item | Item List | — | — | Desktop | productList | Product title click — GA4 ecommerce event, not a listing_page_clicksitems: [{ item_id }] · section_path: Category | observed
New | New Item Category Listing Page Product Card | Product Title | listing_page_clicks | Other Buying Options | Used | 1910936-REG | Desktop | productList | "Used for $39.95" link on a tile — the only component on this page that populates label_valuesection_path: Category · label = buying-option type · label_value = SKU | observed
New | New Item Category Listing Page Product Card | Product Title | listing_page_clicks | Show More | — | — | Desktop | productList | Expanding a tile's Key Featuressection_path: Category — no item_id, so it cannot be tied to a product | F5
New | New Item Category Listing Page Product Card | Product Title | listing_page_clicks | Add to Compare | — | — | Desktop | productList | Compare checkbox on a tile — no label, no item identifier | F5
New |  | Promo & Navigation | select_promotion | — | — | — | Desktop | productList | Hero banner click — mirrors the view_promotion paramscreative_name: IO Image Banner · creative_slot: HERO · promotion_url: /a/trade-in/64435 | observed
New |  | Promo & Navigation | breadcrumbs | Breadcrumb | — | — | Desktop | productList | Breadcrumb link clickbreadcrumbs: Photography — destination in its own param rather than label | observed
New | New Item Category Landing Page | Navigation into the Catalog | category_page_clicks | Category Groups | Cameras & Lenses | Digital Cameras | Desktop | category | Category tile — label is the section, label_value the destinationcategory_page_id: 989 | model
New | New Item Category Landing Page | Navigation into the Catalog | category_page_clicks | Category Groups | Accessories | Lens Accessories | Desktop | category | Same component, second section — the convention holds across the page | model
New | New Item Category Landing Page | Navigation into the Catalog | category_page_clicks | Category Groups | Applications | Portrait Photography | Desktop | category | The "What would you like to shoot?" rail — reports under its internal key, Applicationsthe only section whose label doesn't match its visible heading | C3
New | New Item Category Landing Page | Content & Banners | category_page_clicks | Explora banner | Venus Optics Delivers Two New Ultra-Macro Laowa Lenses | — | Desktop | category | Editorial rail — label carries the full article title, so content performance is readable | observed
New | New Item Category Landing Page | Content & Banners | category_page_clicks | Category Banner | — | — | Desktop | category | The Hasselblad "Learn More" unit — no label, so which brand banner was clicked is unknowable | C2
New | New Item Category Landing Page | Content & Banners | category_page_clicks | chatBanner | — | — | Desktop | category | "Video Chat with a Photography Expert" strip — opens the chat widget, sends nothing about which expert path | C2
New | New Item Category Landing Page | Content & Banners | category_page_clicks | SEO Text | Show More | — | Desktop | category | Expanding the bottom copy block — same component and label as on the listing page | observed
New | New Item Category Landing Page | Promo & Exits | select_promotion | — | — | — | Desktop | category | Trade-in banner clicked — mirrors its impression event exactly, same promotion_idcreative_slot: TOP · promotion_url: /a/trade-in/64435 | observed
New | New Item Category Landing Page | Promo & Exits | select_promotion | — | — | — | Desktop | category | Spotfront product rail item clicked — impression and click share promotion_id and promotion_position, so slot-level CTR is directly computable | observed
New | New Item Category Landing Page | Promo & Exits | footer_clicks | Trade in Your Gear | — | — | Desktop | category | Footer trade-in link — a different event family from the banner above it, same destination | C5
N/A | PDP |  | view_item | — | — | — | Desktop | productDetail | Product rendered — the richest payload on the page, and still condition-blindcurrency: USD · value: 2136.95 · items: [{ item_id: 803528607-USE, item_code: 3528607, price: 2136.95, stock_status: IN_STOCK, shipping_message: FREE_ONE_DAY_DELIVERY, store_pickup_message: AVAILABLE_IN_PICKUP_TIME }] | U1 U5
N/A | PDP |  | view_item | — | — | — | absent | absent | Google Ads remarketing — this one knows it's usedecomm_pcat: ["BH Photo", "Used Department", "Photography", "Point & Shoot Cameras", "Sony RX10 V"] · ecomm_prodid: 803528607-USE · ecomm_totalvalue: 2136.95 | U1
N/A | PDP |  | page_view | — | — | — | Desktop | productDetail | Page load — content_group also productDetail, so neither dimension separates used from newsite_langauge: E · bi: NoValue · pwa_source: NoValue · bh_user_id: id_NoValue | U1
N/A | PDP |  | view_promotion | — | — | — | Desktop | productDetail | Overview banner (an Explora article on this camera) and the email slide-outcreative_slot: Overview Banner / SLIDER · promotion_name · detail_page_sku | observed
Used | Used PDP | Used Specific Interaction | detail_page_clicks | Used Item Condition | — | — | Desktop | productDetail | "Condition: 9 Minor surface marks" → opens the B&H Used Equipment Rating System drawerdetail_page_sku only — the grade the shopper just clicked on is not sent | U2
Used | Used PDP | Used Specific Interaction | detail_page_clicks | Other Buying Options | New | — | Desktop | productDetail | "New for $2,298.00" — the used → new switchno label_value, though the same component on the listing page sends the SKU there | U4
Used | Used PDP | Used Specific Interaction | detail_page_clicks | Trade In - Learn More | — | — | Desktop | productDetail | "Trade in your gear for cash — Get Started" — present and tagged on used PDPs exactly as on new onesdetail_page_sku | observed
Used | Used PDP | Used Specific Interaction | breadcrumbs | Breadcrumb | — | — | Desktop | productDetail | Breadcrumb click — the one place "Used Department" reaches GA4 as a valuebreadcrumbs: "Used Department" · only fires if someone actually clicks it | U6
N/A | PDP | Generic PDP Furniture | detail_page_clicks | searchDropdown | — | — | Desktop | productDetail | The header search scope selector, which is pre-set to "Used" on this page — but the event doesn't say which scope was chosen | U2
N/A | PDP | Generic PDP Furniture | detail_page_clicks | Add to Compare | — | — | Desktop | productDetail | Compare checkbox — carries the SKU here, unlike its listing-page counterpart, which carries nothing | observed
N/A | PDP | Generic PDP Furniture | detail_page_clicks | Tab Navigation | Specs · Reviews · Q&A | — | Desktop | productDetail | Content tabs — not exercised on this page; carried over from the new-PDP audit, where label carried the tab namedetail_page_sku | new PDP
N/A | PDP | Generic PDP Furniture | — | — | — | — | — | — | No event: Share · Print · the "Used Savings $161.05" figure · the "Warranty: B&H 90 Days" line · the 90-Second Intro video badge | U7
New | New Item PDP Trade In Your Gear CTA
N/A | Cart
N/A | Check Out
N/A | My Account |  | category_page_clicks
Used | Used Hub | Landing Page
Used | Used Hub Switcher
Used | Used Hub Category Navigation
Used | Used Hub See Our Rating System | Link
Used | Used Hub Visit Our Used Dept FAQ For Further Details | Link
Used | Used Hub 90 Days Parts And Labor Warranty See Details | Link
Used | Used Hub Free Shipping See Details | Link
Used | Used Hub Sell Your Gear in 3 Easy Steps Video | Video
Used | Used Hub NYC SuperStore | Link
Used | Used Hub Get Started Online CTA | CTA
Used | Used Hub Customer Reviews | Carousel
Used | Used Hub FAQ Search
Used | Used Hub FAQ Title
Used | Used Hub FAQ Description
Used | Used Hub FAQ See All
Used | Used Hub Address
Used | Used Hub Phone Number
Used | Footer Trade In Your Gear | Link
Used | Used Top Nav
Used | Used Mega Menu
Used | Used Mega Menu Category | Mega Menu Category
Used | Used Mega Menu Sell Your Gear | Link
Used | Used Site Search Box | Search Field
Used | Used Site Search Type Ahead | Search Field Type Ahead
Used | Used Category Landing Page | PLP
Used | Used Category Listing Page | PLP
Used | Used Category Listing Page Filter
Used
Used | Used Category Listing Page Product Card | Product Card
Used | Used Category Listing Page Product Card Used From CTA | CTA
Used | Used PDP | PDP
Used | Used Brand Listing Page | PLP
Used | Trade In Page
Used | Sell Used Landing Page
Used | Sell Used Search Box
Used | Sell Used Detail Page
Used | Sell Used Review Page
Used | Sell Used Listing Page
Used | Used Category Landing Page
Used | Used Category Listing Page
N/A | My Account Trade In Module

## Roadmap Calc (Don’t Touch) (hidden)
Weekly Row | Title | Portfolio | Theme | Jira | Status | UX From | UX To | Dev From | Dev To | Product Ticket | Theme Rank | Status Rank | Sort Key | Rank | Dev From Raw | Dev To Raw | Dev From Parsed | Dev To Parsed | UX Weeks | Theme Ctrl Row | Included | Alpha Rank | Theme #2 | Sort Name | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | AUTO-GENERATED HELPER — do not edit. Row r here = UX Weekly row r = Dev Tracker row r. Columns AA-AX flag, per month, whether that month holds at least one resourced UX week. Month names are parsed from a literal string, so nothing here breaks if a row is deleted.
2 | New Condition Rating Scale | Used | Improve Buy Used Customer Experience | BHUX-33510 | 00. Parking Lot | 2026-06-01 | 2026-06-15 | 2027-01-01 | 2027-01-31 | BHP-4771 | 6 | 1 | 6010002 | 22 | Jan 2027 | Jan 2027 | 2027-01-01 | 2027-01-01 | 3 | 9 | 1 | 125 | Improve Trade In User Flow | NEWCONDITIONRATINGSCALE | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | B2B Hub - Logged In B2B Experience | B2B | Increase B2B Acquisition | BHP-6901 | 00. Parking Lot | 2026-06-08 | 2026-10-26 | 2027-03-01 | 2027-05-31 | BHP-6901 | 8 | 1 |  |  | Mar 2027 | May 2027 | 2027-03-01 | 2027-05-01 | 5 | 11 | 0 | 109 |  | B2BHUBLOGGEDINB2BEXPERIENCE | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Theme detail — drives the panel on Roadmap (Auto)
4 | New Condition Rating Scale (Intermediate Step) | Used | Improve Buy Used Customer Experience | BHJ-121278 | 00. Parking Lot |  |  | 2026-10-01 | 2026-10-31 | BHP-7238 | 6 | 1 | 6010004 | 23 | Oct 2026 | Oct 2026 | 2026-10-01 | 2026-10-01 | 0 | 9 | 1 | 126 | Improve Trade In User Flow | NEWCONDITIONRATINGSCALEINTERMEDIATESTEP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Control row | 0
5 | B2B - The Studio Categories | B2B | Improve The Studio B&H Customer Experience | BHUX-33434 | 01. Prod Discovery | 2026-04-20 | 2026-09-14 | 2026-12-01 | 2027-01-31 | BHP-6446 | 10 | 3 |  |  | Dec 2026 | Jan 2027 | 2026-12-01 | 2027-01-01 | 6 | 13 | 0 | 112 |  | B2BTHESTUDIOCATEGORIES | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Description
6 | The Studio - Stand Alone Website | B2B | Increase The Studio B&H Awareness |  | 01. Prod Discovery | 2026-09-07 | 2026-09-21 | 2027-01-01 | 2027-03-31 |  | 9 | 3 |  |  | Jan 2027 | Mar 2027 | 2027-01-01 | 2027-03-01 | 3 | 12 | 0 | 141 |  | THESTUDIOSTANDALONEWEBSITE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Measure adoption
7 | B2B Homepage About Us Module | B2B | Increase B2B Acquisition | BHP-7274 | 01. Prod Discovery |  |  | 2027-02-01 | 2027-02-28 | BHP-7274 | 8 | 3 |  |  | Feb 2027 | Feb 2027 | 2027-02-01 | 2027-02-01 | 0 | 11 | 0 | 107 |  | B2BHOMEPAGEABOUTUSMODULE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Measure impact
8 | Decouple Sell Used from Used Hub | Used | Increase Trade In Awareness | BHP-7431 | 01. Prod Discovery |  |  | 2027-02-01 | 2027-02-28 | BHP-7431 | 2 | 3 | 2030008 | 1 | Feb 2027 | Feb 2027 | 2027-02-01 | 2027-02-01 | 0 | 5 | 1 | 115 |  | DECOUPLESELLUSEDFROMUSEDHUB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Sell Used Mega Menu | Used | Increase Trade In Awareness | BHP-7430 | 01. Prod Discovery | 2026-09-21 | 2026-09-28 |  |  |  | 2 | 3 | 2030009 | 2 |  |  |  |  | 2 | 5 | 1 | 131 |  | SELLUSEDMEGAMENU | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Used Roll Up SKUs | Used | Improve Buy Used Customer Experience | BHP-6479 | 01. Prod Discovery |  |  | 2026-12-01 | 2027-02-28 |  | 6 | 3 | 6030010 | 24 | Dec 2026 | Feb 2027 | 2026-12-01 | 2027-02-01 | 0 | 9 | 1 | 148 |  | USEDROLLUPSKUS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Sell Used Purchase Look Up | Used | Improve Trade In User Flow | BHP-7236 | 02. UX Req | 2026-08-24 | 2026-09-07 | 2026-11-01 | 2027-01-31 | BHP-7236 | 3 | 4 | 3040011 | 7 | Nov 2026 | Jan 2027 | 2026-11-01 | 2027-01-01 | 3 | 6 | 1 | 132 |  | SELLUSEDPURCHASELOOKUP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Used Activity Notification | Used | Increase Trade In Awareness | BHP-7237 | 02. UX Req | 2026-09-14 | 2026-09-28 | 2026-12-01 | 2027-01-31 | BHP-7237 | 2 | 4 | 2040012 | 3 | Dec 2026 | Jan 2027 | 2026-12-01 | 2027-01-01 | 3 | 5 | 1 | 144 |  | USEDACTIVITYNOTIFICATION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | The Studio - Enhanced Landing Page | B2B | Improve The Studio B&H Customer Experience | BHP-6444 | 02. UX Req | 2026-09-07 | 2026-09-21 | 2027-01-01 | 2027-01-31 | BHP-6444 | 10 | 4 |  |  | Jan 2027 | Jan 2027 | 2027-01-01 | 2027-01-01 | 3 | 13 | 0 | 140 |  | THESTUDIOENHANCEDLANDINGPAGE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Used Hub - Just Added Component | Used | Increase Buy Used Awareness | BHP-7229 | 02. UX Req | 2026-08-10 | 2026-09-14 | 2027-02-01 | 2027-02-28 | BHP-7229 | 5 | 4 | 5040014 | 13 | Feb 2027 | Feb 2027 | 2027-02-01 | 2027-02-01 | 3 | 8 | 1 | 146 |  | USEDHUBJUSTADDEDCOMPONENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Used Just Added Page | Used | Increase Buy Used Awareness | BHP-7230 | 02. UX Req | 2026-05-18 | 2026-10-12 | 2027-02-01 | 2027-02-28 | BHP-7230 | 5 | 4 | 5040015 | 14 | Feb 2027 | Feb 2027 | 2027-02-01 | 2027-02-01 | 4 | 8 | 1 | 147 |  | USEDJUSTADDEDPAGE | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Increase Awareness of Trade In Offers - Best Buy Inspiration/Competitive Effort | Used | Increase Trade In Awareness | BHP-6827 | 03. UX Discovery |  |  | 2026-10-01 | 2026-10-31 | BHP-6827 | 2 | 5 | 2050016 | 4 | Oct 2026 | Oct 2026 | 2026-10-01 | 2026-10-01 | 0 | 5 | 1 | 120 |  | INCREASEAWARENESSOFTRADEINOFFERSBESTBUYINSPIRATIONCOMPETITIVEEFFORT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Out of stock Alerts for used products | Used | Increase Buy Used Awareness | BHUX-35020 | 03. UX Discovery | 2026-08-03 | 2026-08-24 | 2026-10-01 | 2026-10-31 | BHP-4792 | 5 | 5 | 5050017 | 15 | Oct 2026 | Oct 2026 | 2026-10-01 | 2026-10-01 | 4 | 8 | 1 | 127 |  | OUTOFSTOCKALERTSFORUSEDPRODUCTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | The Studio - B&H Awareness on High Ticket Items | B2B | Increase The Studio B&H Awareness | BHUX-35304 | 03. UX Discovery | 2026-08-17 | 2026-09-07 | 2026-10-01 | 2026-10-31 | BHP-7239 | 9 | 5 |  |  | Oct 2026 | Oct 2026 | 2026-10-01 | 2026-10-01 | 4 | 12 | 0 | 138 |  | THESTUDIOBHAWARENESSONHIGHTICKETITEMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Add New ¦ Used tab to all listing pages and search results pages | Used | Increase Buy Used Awareness | BHUX-35303 | 03. UX Discovery | 2026-08-24 | 2026-09-14 | 2026-11-01 | 2026-11-30 | BHP-5726 | 5 | 5 | 5050019 | 16 | Nov 2026 | Nov 2026 | 2026-11-01 | 2026-11-01 | 4 | 8 | 1 | 105 | Improve Discovery | ADDNEWUSEDTABTOALLLISTINGPAGESANDSEARCHRESULTSPAGES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | The Studio - Category Hybrid Page | B2B | Increase The Studio B&H Awareness | BHP-7301 | 04. UX Design | 2026-08-10 | 2026-09-07 | 2026-10-01 | 2026-10-31 | BHP-7301 | 9 | 6 |  |  | Oct 2026 | Oct 2026 | 2026-10-01 | 2026-10-01 | 4 | 12 | 0 | 139 |  | THESTUDIOCATEGORYHYBRIDPAGE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Highlighted Refinements Enhancement | Find | Improve Discovery | BHUX-35302 | 04. UX Design | 2026-08-24 | 2026-09-14 | 2026-10-01 | 2026-10-31 | BHP-7266 | 1 | 6 |  |  | Oct 2026 | Oct 2026 | 2026-10-01 | 2026-10-01 | 4 | 4 | 0 | 119 |  | HIGHLIGHTEDREFINEMENTSENHANCEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Trade In Email - Comprehensive Refresh Discovery | Used | Improve Trade In User Flow | BHUX-34772 | 04. UX Design | 2026-07-13 | 2026-08-03 | 2026-10-01 | 2026-10-31 | BHP-6391 | 3 | 6 | 3060022 | 8 | Oct 2026 | Oct 2026 | 2026-10-01 | 2026-10-01 | 4 | 6 | 1 | 143 |  | TRADEINEMAILCOMPREHENSIVEREFRESHDISCOVERY | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Used - Sell Used Experience | Used | Improve Trade In User Flow | BHUX-33009 | 04. UX Design | 2026-04-20 | 2026-09-28 | 2027-01-01 | 2027-03-31 | BHP-6434 | 3 | 6 | 3060023 | 9 | Jan 2027 | Mar 2027 | 2027-01-01 | 2027-03-01 | 24 | 6 | 1 | 149 |  | USEDSELLUSEDEXPERIENCE | 0 | 0 | 0 | 2 | 4 | 5 | 4 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Add 'shop by popular brands' section to Used Homepage | Used | Increase Buy Used Awareness | BHUX-34844 | 04. UX Design | 2026-07-20 | 2026-09-07 | 2026-11-01 | 2027-01-31 | BHP-6735 | 5 | 6 | 5060024 | 17 | Nov 2026 | Jan 2027 | 2026-11-01 | 2027-01-01 | 8 | 8 | 1 | 106 |  | ADDSHOPBYPOPULARBRANDSSECTIONTOUSEDHOMEPAGE | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Shop By Popular Brand' Listing Pages Discovery | Used | Increase Buy Used Awareness | BHUX-34845 | 04. UX Design | 2026-07-27 | 2026-09-07 | 2026-11-01 | 2027-01-31 | BHP-6735 | 5 | 6 | 5060025 | 18 | Nov 2026 | Jan 2027 | 2026-11-01 | 2027-01-01 | 7 | 8 | 1 | 134 |  | SHOPBYPOPULARBRANDLISTINGPAGESDISCOVERY | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | My Account > Trade In Awareness | Used | Increase Buy Used Awareness | BHUX-35010 | 04. UX Design | 2026-08-10 | 2026-08-24 | 2026-12-01 | 2026-12-31 | BHP-7196 | 5 | 6 | 5060026 | 19 | Dec 2026 | Dec 2026 | 2026-12-01 | 2026-12-01 | 3 | 8 | 1 | 122 |  | MYACCOUNTTRADEINAWARENESS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | B2B & Used Visibility in the Nav | B2B/Used | Increase Trade In Awareness | BHUX-34378 | 04. UX Design | 2026-06-01 | 2026-09-28 | 2027-02-01 | 2027-02-28 | BHP-6900 | 2 | 6 | 2060027 | 5 | Feb 2027 | Feb 2027 | 2027-02-01 | 2027-02-01 | 18 | 5 | 1 | 113 | Increase B2B Acquisition | B2BUSEDVISIBILITYINTHENAV | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Sell Used User Flow Design Validation | Used | Improve Trade In User Flow | BHUR-133 | 04A. Research - Design Validation | 2026-07-06 | 2026-09-07 |  |  | BHP-6434 | 3 | 7 | 3070028 | 10 |  |  |  |  | 10 | 6 | 1 | 133 |  | SELLUSEDUSERFLOWDESIGNVALIDATION | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Used Status Email Update | Used | Improve Trade In User Flow | BHUX-34723 | 06. Architecture | 2026-07-13 | 2026-07-13 | 2026-10-01 | 2026-10-31 | BHP-7145 | 3 | 9 | 3090029 | 11 | Oct 2026 | Oct 2026 | 2026-10-01 | 2026-10-01 | 1 | 6 | 1 | 150 |  | USEDSTATUSEMAILUPDATE | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | PDP Purchased in 20XX, Trade In Value is $YYY.YY | Used | Increase Trade In Awareness | BHUX-35309 | 06. Architecture | 2026-08-17 | 2026-08-17 | 2026-10-01 | 2026-10-31 | BHP-7228 | 2 | 9 | 2090030 | 6 | Oct 2026 | Oct 2026 | 2026-10-01 | 2026-10-01 | 1 | 5 | 1 | 128 |  | PDPPURCHASEDIN20XXTRADEINVALUEISYYYYY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | B2B Hub Landing Page - redesign | B2B | Increase B2B Acquisition | BHUX-26541 | 07. Grooming | 2026-04-13 | 2026-05-11 | 2026-10-01 | 2026-12-31 |  | 8 | 10 |  |  | Oct 2026 | Dec 2026 | 2026-10-01 | 2026-12-01 | 5 | 11 | 0 | 108 |  | B2BHUBLANDINGPAGEREDESIGN | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | B2B Hub - Revisit Signup Flow | B2B | Increase B2B Acquisition | BHUX-31874 | 07. Grooming | 2026-04-13 | 2026-05-25 | 2026-10-01 | 2026-12-31 |  | 8 | 10 |  |  | Oct 2026 | Dec 2026 | 2026-10-01 | 2026-12-01 | 7 | 11 | 0 | 111 |  | B2BHUBREVISITSIGNUPFLOW | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | B2B Hub Redesign - Internal Pages | B2B | Increase B2B Acquisition | BHUX-32257 | 07. Grooming | 2026-04-20 | 2026-05-11 | 2026-10-01 | 2026-12-31 |  | 8 | 10 |  |  | Oct 2026 | Dec 2026 | 2026-10-01 | 2026-12-01 | 4 | 11 | 0 | 110 |  | B2BHUBREDESIGNINTERNALPAGES | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Nested Refinements | Find | Improve Discovery | BHUX-32621 | 08. Ready for Dev |  |  | 2026-10-01 | 2026-10-31 | BHP-2802 | 1 | 11 |  |  | Oct 2026 | Oct 2026 | 2026-10-01 | 2026-10-01 | 0 | 4 | 0 | 124 |  | NESTEDREFINEMENTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | Mega Menu | Find | Improve Discovery | BHUX-29580 | 09. In Dev | 2026-04-27 | 2026-06-01 | 2026-09-01 | 2026-09-30 | BHUX-29580 | 1 | 12 |  |  | Sep 2026 | Sep 2026 | 2026-09-01 | 2026-09-01 | 3 | 4 | 0 | 121 |  | MEGAMENU | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | School Safety Landing Page | B2B | Increase B2B Acquisition | BHUX-34377 | 09. In Dev | 2026-06-15 | 2026-08-10 | 2026-09-01 | 2026-09-30 | BHP-5830 | 8 | 12 |  |  | Sep 2026 | Sep 2026 | 2026-09-01 | 2026-09-01 | 9 | 11 | 0 | 130 |  | SCHOOLSAFETYLANDINGPAGE | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | Sunset Modals for Drawers | Find | Improve Discovery | BHUX-32543 | 09. In Dev |  |  | 2026-08-01 | 2026-08-31 | BHP-6228 | 1 | 12 |  |  | Aug 2026 | Aug 2026 | 2026-08-01 | 2026-08-01 | 0 | 4 | 0 | 137 |  | SUNSETMODALSFORDRAWERS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | Trade In Discrepancy Email Refresh (Copy Only) | Used | Improve Trade In User Flow |  | 09. In Dev | 2026-07-13 | 2026-07-20 | 2026-09-01 | 2026-09-30 |  | 3 | 12 | 3120038 | 12 | Sep 2026 | Sep 2026 | 2026-09-01 | 2026-09-01 | 2 | 6 | 1 | 142 |  | TRADEINDISCREPANCYEMAILREFRESHCOPYONLY | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | Condition Grouping | Used | Increase Buy Used Awareness | BHUX-33519 | 13. Live | 2026-04-27 | 2026-05-04 | 2026-08-01 | 2026-08-31 | BHP-4518 | 5 | 16 | 5160039 | 20 | Aug 2026 | Aug 2026 | 2026-08-01 | 2026-08-01 | 2 | 8 | 1 | 114 |  | CONDITIONGROUPING | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | Sliders | Find | Improve Discovery | BHUX-17615 | 13. Live |  |  |  |  | BHP-3757 | 1 | 16 | [6 empty] | 0 | 4 | 0 | 135 |  | SLIDERS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | Refinement - Select All/Deselect All | Find | Improve Discovery | BHUX-23755 | 13. Live |  |  |  |  | BHP-2638 | 1 | 16 | [6 empty] | 0 | 4 | 0 | 129 |  | REFINEMENTSELECTALLDESELECTALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | My Gear 2 - Tray | Find | Improve Discovery | BHUX-28124 | 13. Live |  |  |  |  | BHP-5060 | 1 | 16 | [6 empty] | 0 | 4 | 0 | 123 |  | MYGEAR2TRAY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | H2 on listing pages | Find | Improve Discovery | BHUX-31245 | 13. Live |  |  |  |  | MRCH-2202 | 1 | 16 | [6 empty] | 0 | 4 | 0 | 117 |  | H2ONLISTINGPAGES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | Sunset Dealzone | Find | Improve Discovery | BHUX-32071 | 13. Live |  |  |  |  | BHJ-119850 | 1 | 16 | [6 empty] | 0 | 4 | 0 | 136 |  | SUNSETDEALZONE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | Highlighted Refinements | Find | Improve Discovery | BHUX-29921 | 13. Live |  |  |  |  | BHP-5132 | 1 | 16 | [6 empty] | 0 | 4 | 0 | 118 |  | HIGHLIGHTEDREFINEMENTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | EDU Homepage | B2B | Increase B2B Acquisition | BHUX-25601 | 13. Live | 2026-05-04 | 2026-06-15 | 2026-08-01 | 2026-08-31 | BHP-3583 | 8 | 16 |  |  | Aug 2026 | Aug 2026 | 2026-08-01 | 2026-08-01 | 2 | 11 | 0 | 116 |  | EDUHOMEPAGE | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | Actual Used Images | Used | Improve Buy Used Customer Experience | BHP-4563 | 13. Live |  |  |  |  | BHP-4563 | 6 | 16 | 6160047 | 25 |  |  |  |  | 0 | 9 | 1 | 104 |  | ACTUALUSEDIMAGES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | Used Hub Enhancements | Used | Increase Buy Used Awareness | BHUX-31354 | 13. Live |  |  |  |  | BHP-5817 | 5 | 16 | 5160048 | 21 |  |  |  |  | 0 | 8 | 1 | 145 |  | USEDHUBENHANCEMENTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0