## Sheet1
Title | Status | Portfolio | Component | Tech | Start Sprint | End Sprint | Notes
Post Hub | 0. Discovery | B2B | B2B Hub | BHJ | Oct | Jan | Deprioritized by Ariel until visibility in the Nav is addressed
School Safety Landing Page | 2. Design | B2B | B2B Hub Plus | BHJ | Sep | Sep | The majority of the design is complete, Additional content was requested by UX, delivered by Product 7/9
Sell Used | 2B. Research | Used Operations | Cart | UNIX, BHJ, SEARCH | Sep | Jan | Research transitioned from Birdie to Hanna, pausing for ramp up
New Condition Rating Scale | 3. Architecture | Used Operations | PLP/PDP | UNIX, BHJ | Aug | Aug | User Testing cancelled, too many concurrent points of friction with UX, compromising for the sake of progress. Isaac checking with Yosi Gross for approval on UX's new path.
Mega Menu | 3. Architecture | Merchandising | Navigation | BHJ, BHIA, BIDW | Aug | Oct | Four technical ideation meetings booked, two complete, Progress being made with tech reqs
Nested Refinements | 4. Dev | Web Experience | PLP/Search | BHJ, BHIA, SEARCH | Sep | Nov | Multiple Prerequisites and dependencies: BHIA, BHJs
EDU Homepage | 4. Dev | B2B | EDU | BHJ | Aug | Aug
Group by Conditon | 4. Dev | Used Operations | PLP/PDP | BHJ | Jun | Jul | Met with architecture, requirements confirmed, moving forward with dev
My Gear Release 2 | 4. Dev | Web Experience | My Gear | BHJ, BHIA, SEARCH
Highlighted Refinements | 4. Dev | Merchandising | PLP/Search | BHJ, Search, BHIA | May | Jul | Operationalizing with Shalom Oster & Daniel Ballas, should be live late June, currently in Pull Request
B2B Hub | 4. Dev | B2B | B2B Hub | BHJ
Actual Used Images | 5. Implementation | Used Operations | PDP/ Images | BHJ, BHIA | Mar | Jun | Reached out to Isaac to make the Ortery Purchase
Sunset Deal Zone | 7. Live | Web Experience | Navigation | BHJ | Jun | Aug | Almost complete, need Permalink and nav jiras live
View All Category Landing Page | 7. Live | Web Experience | Category Landing Page | BHJ, BHIA |  | Jul | Approved UAT; operationalizing with nav arcs
Roll Up SKUs | 99. Parking Lot | Web Experience | PLP/Search | BHJ, BHIA, SEARCH
B2B The Studio Categories | 99. Parking Lot | B2B | B2B Hub | BHJ |  |  | Impeded by stakehodler availability